SWARM-X

Sprint Schedule

April 13 → April 25, 2025

Goal: One robot doing autonomous mapping by April 25th

| 💻 SOFTWARE TEAM — Can work at home April 13–19 + April 22, 23, 24 | 🔧 HARDWARE TEAM — College only April 13, 15, 16, 17, 18 + April 22, 23, 24 |
| --- | --- |

□ = task to complete    → = detail / sub-step    ✅ = end of day checkpoint

💻 SOFTWARE TEAM SCHEDULE

Sunday, April 13 Day 1 — SOFTWARE — At Home 🎯 Goal: ROS2 environment verified, simulation running

All 3 members — individually - Test the publisher and subscriber node already written - Run it in two terminals, confirm messages appear - If it fails: fix it today. Do not carry bugs forward. - Install Nav2, SLAM, Gazebo, TurtleBot3 sudo apt install ros-humble-navigation2 ros-humble-nav2-bringup ros-humble-slam-toolbox sudo apt install ros-humble-gazebo-ros-pkgs sudo apt install ros-humble-turtlebot3* echo "export TURTLEBOT3_MODEL=burger" >> ~/.bashrc && source ~/.bashrc - Launch TurtleBot3 simulation ros2 launch turtlebot3_gazebo turtlebot3_world.launch.py - Confirm a virtual robot appears in a simulated world on all 3 laptops

✅ End of day check: All 3 laptops running Gazebo with TurtleBot3 visible on screen.

Monday, April 14 Day 2 — SOFTWARE — At Home 🎯 Goal: Autonomous navigation working in simulation

Person 1 — Swarm Lead - Launch SLAM in simulation and drive to build a map ros2 launch turtlebot3_cartographer cartographer.launch.py use_sim_time:=True ros2 run turtlebot3_teleop teleop_keyboard - Save the map ros2 run nav2_map_server map_saver_cli -f ~/swarmx_map

Person 2 — Nav2 Lead - Launch Nav2 with the saved map - Click a goal point in RViz2, watch robot navigate there autonomously — no keyboard - Document every command used — this becomes your hardware cheat sheet

Person 3 — Motor Control Lead - Write motor_driver.py ROS2 node from scratch (do not copy-paste, type it) - Node subscribes to /cmd_vel, converts to left/right PWM signals - Use RPi.GPIO library: pip3 install RPi.GPIO - Forward command → both motors forward - Turn left → right motor faster than left - Cannot test on hardware yet — write and review logic only

✅ End of day check: Persons 1+2 have seen autonomous navigation in simulation. Person 3 has motor_driver.py written and reviewed.

Tuesday, April 15 Day 3 — SOFTWARE — At Home 🎯 Goal: Ultrasonic node tested, motor logic verified

Person 1 — Autonomous goal sending - Write a Python script that sends robot to 3 coordinates automatically without clicking RViz2 - This teaches programmatic goal-sending — critical for autonomous behaviour - Install: sudo apt install ros-humble-nav2-simple-commander

Person 2 — Ultrasonic pipeline - Wrap the ultrasonic framework in a proper ROS2 publisher node - Publishes to /ultrasonic_front and /ultrasonic_back every 0.5 seconds - Write a safety node: if any reading below 30cm, publish STOP to /safety_alert - Test both nodes together with simulated fake distance values — confirm alert fires

Person 3 — Motor logic verification - Review motor_driver.py with Person 1 - Write a test script: simulate receiving /cmd_vel messages, print what PWM values would be sent - Verify the math: forward → both motors same speed, turn left → right motor faster

✅ End of day check: Ultrasonic pipeline tested end-to-end with fake values. Motor logic verified mathematically by 2 people.

Wednesday, April 16 Day 4 — SOFTWARE — At Home 🎯 Goal: Two-robot simulation running, Foxglove dashboard connected

All 3 — Video call together - Study ROS2 namespaces — read this fully: - docs.ros.org/en/humble/Tutorials/Intermediate/Launch/Using-ROS2-Launch-For-Large-Projects.html - Launch two TurtleBot3 robots in the same Gazebo world - github.com/ROBOTIS-GIT/turtlebot3_simulations — multi-robot section - Confirm /robot1/scan and /robot2/scan are separate topics

Person 3 — Dashboard setup - Install and launch rosbridge sudo apt install ros-humble-rosbridge-suite ros2 launch rosbridge_server rosbridge_websocket_launch.xml - Download Foxglove Studio from foxglove.dev - Connect Foxglove to: ws://localhost:9090 - Add a Map panel showing /map topic — confirm simulated robot's map is visible

✅ End of day check: Two simulated robots running with /robot1/ and /robot2/ namespaces. Foxglove connected and showing live map.

Thursday, April 17 Day 5 — SOFTWARE — At Home 🎯 Goal: All code that goes on the Pi written and reviewed

Person 1 — Launch file - Write robot1_launch.py — starts everything with one command - Includes: motor driver, ultrasonic node, safety node, RPLidar driver, SLAM, Nav2 - All topics under /robot1/ namespace

Person 2 — MLX90614 thermal sensor node - Install library: pip3 install adafruit-circuitpython-mlx90614 - Write sensor node: reads temperature every 0.5 seconds, publishes to /robot1/heat_sensor - Add alert logic: if reading exceeds 32°C, publish SURVIVOR_DETECTED to /robot1/alerts - Cannot test on hardware yet — write and review logic only

Person 3 — Dashboard layout - Set up Foxglove Studio panels for demo day: - Large map panel centre - Alerts panel right side - Robot status top bar - Export layout as a JSON file — ready to load on demo day, no setup needed

✅ End of day check: Launch file, sensor node, and dashboard layout all written, pushed to GitHub, and reviewed by at least one other person.

Friday, April 18 Day 6 — SOFTWARE — At Home 🎯 Goal: Full simulation demo rehearsed, startup checklist written

All 3 — Full rehearsal together (video call) - Run the complete simulation pipeline as if it is demo day - Two robots in Gazebo - Both doing frontier exploration - Foxglove showing merged map - Time the full run — how long does mapping take? - Identify every step that could go wrong and write it down - Write a startup checklist: every command in order, every terminal labelled - This document goes to demo day — you read from it, you don't rely on memory

✅ End of day check: Written startup checklist exists. Full simulation pipeline runs without errors. Every team member knows every step.

Saturday, April 19 Day 7 — SOFTWARE — At Home 🎯 Goal: Prepared for hardware integration, GitHub repo live

Person 1 — RPLidar prep - Read the RPLidar ROS2 driver README fully: github.com/Slamtec/rplidar_ros - Write down: exact launch command, topic name, how to verify it works

Person 2 — Raspberry Pi setup prep - Study how to SSH into Raspberry Pi: raspberrypi.com/documentation/computers/remote-access.html - Write a Pi setup checklist: flash OS, enable SSH, connect WiFi, install ROS2, install packages - This gets executed on Monday with real hardware

Person 3 — GitHub setup - Create SWARM-X GitHub repository, invite all 6 team members - Create folder structure: /robot1 /robot2 /central /dashboard - Push all code written this week - From now on: every change goes to GitHub. No code lives only on one person's laptop.

✅ End of day check: GitHub repo live with all code. RPLidar launch understood. Pi setup checklist written.

🔧 HARDWARE TEAM SCHEDULE

Sunday, April 13 Day 1 — HARDWARE — At College 🎯 Goal: Every component understood, box layout planned

All 3 — Component familiarisation - Unbox everything. Name every component out loud, match to component list. - Watch before touching anything: - 'Raspberry Pi GPIO explained' — any YouTube video, 10-15 mins - 'L298N motor driver tutorial' — LastMinuteEngineers.com - DO NOT connect any power yet - Plan the plastic box layout on paper: - Where does the Pi sit? - Where does L298N sit? - Where do batteries go? - How do motor wires route out? - Everyone agrees on the layout before any cutting or drilling

✅ End of day check: Everyone can name every component and explain what it does. Box layout sketched and agreed by all 3.

Tuesday, April 15 Day 2 — HARDWARE — At College 🎯 Goal: Motors tested, Pi booted, GPIO wired

Person 1 — Motor testing - Wire L298N to motors — no Pi yet, use a 9V battery temporarily - Manually pull IN1 HIGH using jumper wire connected to 5V → motor should spin - Test all 4 motors individually - Confirm direction: which wire combo = forward vs backward - Note down the correct wiring for each motor

Person 2 — Flash Raspberry Pi - Flash Raspberry Pi OS (64-bit) to MicroSD using Raspberry Pi Imager - In Imager settings before flashing: - Enable SSH - Set username: swarmx - Set password: swarmx123 - Set WiFi to your phone hotspot SSID and password - Boot Pi, find it on network: ping swarmx.local - SSH in: ssh swarmx@swarmx.local - Update: sudo apt update && sudo apt upgrade -y

Person 3 — GPIO wiring - Wire L298N signal pins to Raspberry Pi GPIO (signal wires only, no power yet): - IN1 → GPIO 17 - IN2 → GPIO 18 - IN3 → GPIO 27 - IN4 → GPIO 22 - L298N GND → Pi GND - Double-check every connection before Pi is powered on

✅ End of day check: All 4 motors confirmed spinning. Pi booted and SSH working from a laptop. GPIO signal wiring complete and verified.

Wednesday, April 16 Day 3 — HARDWARE — At College 🎯 Goal: Pi controls motors, robot drives with keyboard

All 3 — ROS2 on Pi + motor control - Install ROS2 Humble on Pi (same steps as laptops) - docs.ros.org/en/humble/Installation/Ubuntu-Install-Debs.html - Takes 30-45 minutes. While it installs, install RPi.GPIO: pip3 install RPi.GPIO - Clone GitHub repo onto Pi: git clone [your repo URL] - Run motor_driver.py: ros2 run your_package motor_driver - From laptop on same WiFi, run keyboard teleop: - ros2 run teleop_twist_keyboard teleop_twist_keyboard - Arrow keys should move the robot - Test all directions: forward, backward, left turn, right turn - Tape a straight line on floor, drive robot along it, measure drift over 1 metre - If it veers: adjust PWM values in motor_driver.py until it drives straight

✅ End of day check: Robot moves in all 4 directions from keyboard. Drives roughly straight on flat floor without drifting badly.

Thursday, April 17 Day 4 — HARDWARE — At College 🎯 Goal: RPLidar running, LiDAR scan visible in RViz2

Person 1 — RPLidar setup - Connect RPLidar to Pi via USB - Install driver: sudo apt install ros-humble-rplidar-ros - Find USB port: ls /dev/ttyUSB* → should show ttyUSB0 - Set permissions: sudo chmod 777 /dev/ttyUSB0 - Launch: ros2 launch rplidar_ros rplidar_a1_launch.py - Echo data: ros2 topic echo /scan → numbers should stream

Person 2 — RViz2 visualisation - Open RViz2 on laptop connected to same WiFi - Add LaserScan display, set topic to /scan - Move robot with keyboard, watch dots update in real time - Red dots should form the outline of the room around the robot

Person 3 — HC-SR04 ultrasonics - Connect HC-SR04 to Pi GPIO - VCC → 5V, GND → GND - TRIG → any GPIO output pin - ECHO → any GPIO input pin (use voltage divider: Pi GPIO is 3.3V, HC-SR04 echo is 5V) - Run ultrasonic node from GitHub - Confirm /ultrasonic_front publishing distance readings

✅ End of day check: LiDAR scan visible as red dots in RViz2. Ultrasonic publishing distance readings. Both confirmed working at the same time.

Friday, April 18 Day 5 — HARDWARE — At College 🎯 Goal: Obstacle avoidance working — robot stops before hitting walls

All 3 — Obstacle avoidance integration - Launch motor driver + LiDAR + ultrasonic nodes simultaneously - Add obstacle avoidance to motor driver: - If any LiDAR reading in forward 45° arc is below 40cm → override velocity to zero - If path is clear → pass command through normally - Test 1: Drive robot toward a wall with keyboard → it must stop before hitting - Test 2: Drive in open space → it must NOT false-stop - Run each test 5 times. Fix any failures between runs. - This may take the full day. Do not rush it.

✅ End of day check: Robot stops automatically within 40cm of any wall. Does not stop in open space. Tested 5 times each. This milestone unlocks SLAM next week.

🤝 COMBINED TEAM — April 22, 23, 24

Both teams work together at college these three days. Software team SSHes into the Pi the moment hardware team has it powered on. Debug together in real time.

Monday, April 22 Combined Day 1 — BOTH TEAMS — At College 🎯 Goal: SLAM running, complete room map saved

Full team together - Hardware team: power on robot, confirm all systems running - Software team: SSH into Pi, launch everything from startup checklist - Launch SLAM: ros2 launch slam_toolbox online_async_launch.py - Drive robot manually around the lab room using keyboard - Drive slowly — fast movement makes the map noisy - Cover every corner of the room - Watch map build in RViz2 on laptop - Save the map: ros2 run nav2_map_server map_saver_cli -f ~/lab_map

✅ End of day check: Complete map of the lab room saved. Walls visible as black lines, open space as white, no major gaps.

Tuesday, April 23 Combined Day 2 — BOTH TEAMS — At College 🎯 Goal: Autonomous navigation to clicked goals working

Full team together - Launch Nav2 with saved map - In RViz2: set initial robot pose with '2D Pose Estimate' - Click a destination with '2D Nav Goal' → robot should drive there autonomously - Try 10 different goal points around the room - Note which ones fail and why - Adjust if robot gets stuck or clips walls: - Increase inflation_radius to 0.3 in Nav2 costmap config - This whole day is about making navigation reliable, not just working once

✅ End of day check: Robot navigates autonomously to at least 8 out of 10 clicked goal points successfully.

Wednesday, April 24 Combined Day 3 — DRESS REHEARSAL — BOTH TEAMS — At College 🎯 Goal: Full autonomous exploration, demo rehearsed 3 times

Full team together - Install explore_lite: sudo apt install ros-humble-explore-lite - Launch everything: LiDAR + motor control + SLAM + Nav2 + explore_lite - Robot begins exploring the room by itself — zero keyboard input - Watch in RViz2 as it maps unknown space autonomously - Run the full demo sequence 3 times: - Robot starts at entry point - You launch the software - Robot maps the room autonomously - Time each run - Fix anything that fails between runs - No new features today. Only reliability.

✅ End of day check: Robot autonomously maps the lab room in under 15 minutes, at least 2 out of 3 runs successful. You are ready for tomorrow.

🏆 APRIL 25 — SHORTLISTING DEMO What you show: Robot sits at one end of the room. You launch the software. It starts moving and mapping the space autonomously. No keyboard. No human control. What you say: "This is one robot of a two-robot swarm. It autonomously maps unknown environments using LiDAR and ROS2. The second robot will be built after shortlisting. Together they will coordinate to detect survivors in disaster scenarios." ⚠ You do NOT need two robots for April 25. One robot mapping autonomously is enough to get shortlisted.

The Rules

| 1 | Do not move to the next day's task until today's end-of-day check passes. If the check fails, fix it before moving forward. Bugs compound. |
| --- | --- |

| 2 | No new features after April 24. If it's not built by April 24, it doesn't exist for the demo. Stability beats ambition. |
| --- | --- |

| 3 | Every line of code goes to GitHub the day it's written. If a laptop dies, the project survives. If it's only local, it doesn't. |
| --- | --- |

| 4 | Hardware team: never connect power without double-checking wiring first. One wrong connection can fry a Raspberry Pi worth ₹3,800. Check twice, power once. |
| --- | --- |

| 5 | If stuck for more than 2 hours on the same problem: stop and ask for help. Stack Overflow, ROS Discourse (discourse.ros.org), and YouTube are your first resources. |
| --- | --- |

13 days. 1 robot. Fully autonomous.

Follow the checklist. Test everything. Show up on April 25th.